## Sheet1
SportsCom
Description of Services | Candidate (units) | Candidate (net amount)
Semester 2 (M7-M12)
Maintenance of Social Media & Website (Publish press releases/web articles/social media / Newsletter content)
Gather dissemination partners’ data and produce Semester's Communication Report
Prepare 1st Nesletter
Production of 2 videos (1 inception video + 1 short video from semester exchange activities)
Semester 3 (M13-M18)
Maintenance of Social Media & Website (Publish press releases/web articles/social media / Newsletter content)
Gather dissemination partners’ data and produce Semester's Communication Report
Prepare 2nd Newsletter
Creation of the 2nd short project video on semester exchanged activities
Semester 4 (M19-M24)
Maintenance of Social Media & Website (Publish press releases/web articles/social media / Newsletter content)
Gather dissemination partners’ data and produce Semester's Communication Report
Prepare the 3rd Newsletter
Creation of the 3rd short project video on semester exchanged activities
Semester 5 (M25-M30)
Maintenance of Social Media & Website (Publish press releases/web articles/social media / Newsletter content)
Gather dissemination partners’ data and produce Semester's Communication Report
Prepare 4th Newsletter
Creation of the 4th short project video on semester exchanged activities
Semester 6 (M31-M36)
Maintenance of Social Media & Website (Publish press releases/web articles/social media / Newsletter content)
Gather dissemination partners’ data and produce Semester's Communication Report
Prepare the 5th Newsletter
Creation of the 5th short project video on semester exchanged activities
Semester 7 (M37-M42)
Maintenance of Social Media & Website (Publish press releases/web articles/social media / Newsletter content)
Gather dissemination partners’ data and produce Semester's Communication Report
Creation of the 6th final short project video on semester exchanged activities
Prepare the 6th Newsletter
Semester 8 (M43-M48)
Maintenance of Social Media & Website (Publish press releases/web articles/social media / Newsletter content)
Gather dissemination partners’ data and produce Semester's Communication Report
Prepare the 7th Newsletter
Total Net |  | 0
VAT
TOTAL